## Status
Status of FAS integration

	Project	SA/BA	Aprox Completion Date	Req. Date
1	MFUND	ALANKAR VERMA	15 Oct 11	21804
2	PMS	PRANAV R DESAI	13 Sep 11	21803
3	Customer Care	CHINTAN N JARIWALA	16 Sep 11	21802
4	PortfolioPlus	HARSHIT S. SONI	31 Oct 11	21798
5	RAP	ALANKAR VERMA	15 Sep 11	21814

## Schedule
Req id	Req Title	Project	post by (SA/BA)	priority
21804	R&D initiative request for implementing web service to uniform FAS product insert logic	MFUND	ALANKAR VERMA	7
21803	R&D initiative request for implementing web service to uniform FAS product insert logic	PMS	PRANAV R DESAI	6
21802	R&D initiative request for implementing web service to uniform FAS product insert logic	Customer Care	CHINTAN N JARIWALA	3
21798	System Integration of Portfolioplus with othe projects	PortfolioPlus	HARSHIT S. SONI	19
21814	R&D initiative request for implementing web service to uniform FAS product insert logic	RAP	ALANKAR VERMA	3

	On Date 09-08-2011

21804	this would be sep end /oct first week	MFUND	ALANKAR VERMA
21803	we will be probably starting it by first week of next month	PMS	PRANAV R DESAI
21802	Development will start from 17-08-2011	Customer Care	CHINTAN N JARIWALA
21798	aug end – final deployment	PortfolioPlus	HARSHIT S. SONI
21814	need to discuss with Bhavin sir, as RAP will be a part of PSS so, changes will cover in PSS req which will be analyzed in mid of sep	RAP	ALANKAR VERMA

	On Date 29-08-2011

21804	is in requested state target would be 15 Oct (+/- 10 days )	MFUND	ALANKAR VERMA
21803	SEP-13 final deployment	PMS	PRANAV R DESAI
21802	SEP-16 final deployment	Customer Care	CHINTAN N JARIWALA
21798	OCT end – final deployment	PortfolioPlus	HARSHIT S. SONI
21814	is in analysis , target would be 15 sep (+/- 1 Week )	RAP	ALANKAR VERMA