## RND-CONTINUE
Category	subcategory	Task	DOER	status
Rapid Application Development	IDE / RAD Tool / Plugins	Spring Roo	Bhatu	Continue
Rapid Application Development	IDE / RAD Tool / Plugins	APEX	Bhatu	Continue
RND	Initiative of New Technology	Thread Level Information in Tomcat	Bhatu	Continue
RND	Initiative of New Technology	Tomcat Parameters and Configuration Study	Bhatu	Continue
RND	Initiative of New Technology	Study and Implement EJB	Nirali	Continue
RND	Initiative of New Technology	Study and Implement WS Local Transport	Nirali	Continue
RND	Initiative of New Technology	Study and Implement Spring RMI	Nirali	Continue
RND	Initiative of New Technology	TikiWiki	Nirali	Continue
Application Architecture	Support	Change in karvy Auto Statement Utility of Customer Care	Nirali	Continue

## RND-COMPLETED
Category	Sub-Category	Task	Doer	Status	Month			Mode
Integration	service implementation	SMS Service configured, implemented and deployed.	Bhatu	Done	Jul			Accountable
Integration	Integration	provided design/arhitecture for change in upfront income report to solve delay	Bhatu	Done	Jul	execution of data fetchin on infobright		Doer
Integration	service implementation	Email Service configured, implemented and deployed.	Bhatu	Done	Jul
Integration	service implementation	Upfront Income Service configured, implemented and deployed.	Bhatu	Done	Jul
Application Architecture	Support	Solving sms service regarding PHP timeout	Bhatu	Done	Aug
Application Architecture	Support	Deploying fas service on production	Bhatu	Done	Aug
Application Architecture	Support	Support to Sweta for PartnerLocation DataManager Creation.	Bhatu	Done	Aug
Application Architecture	Support	Studying FAS Ledger Report Generation Utility for Improvement.	Bhatu	Done	Aug
Application Architecture	Support	Tanzim – meeting regarding email from partner desk	Bhatu	Done	Jul
Application Architecture	Support	KYD status run – ARN validity check on third party site	Bhatu	Done	Jul
Application Architecture	Support	technical solution for partner desk bulk mail	Bhatu	Done	Jul
Application Architecture	Support	Support in Jasper Report for BIMS project	Bhatu	Done	Jul
Application Architecture	Support	initiative for restrict direct access to storage box (for image viewing)	Bhatu	Done	Jul
Application Architecture	Support	utility for access storage box & file management - common project for bulkdata	Bhatu	Done	Jul
Application Architecture	Support	utility for log rotation – now switched to infrastucture dept	Bhatu	Done	Jul
Server	Monitoring	Zapcat and Zabbix setting for all tomcat servers	Bhatu	Done	Aug
Server	setup	Mule ESB – implemented and deployed on all servers	Bhatu	Done	Jul
Integration	service implementation	Working for DP Secure Login for HTTP service – LDAP/ACL integration	Bhatu	Done	Aug
RND	Support	redesign faz report (rptgenledger) with technical improvement which use 100% CPU.	Bhatu	Done	Aug	Now it comes in 15 mins
Server	Configuration/Updation	Tomcat other than root user, configured on finserver, njtest2 and njtest-tomcat2	Bhatu	Done	Aug
Server	Configuration/Updation	Tomcat7 update on all production server	Bhatu	Done	Aug
Server	deployment	Mule configuration for bims and ciadesk on dev, test and prod server	Bhatu	Done	Aug
Server	deployment	Creating svn repository – store, fileaccess, salesprocess	Bhatu	Done	Aug
RND	server	Study JVM parameters, configuraed on dev, test and prod servers	Bhatu	Done	Aug
Server	deployment	Creating email-alias - e-report@njecare.com , info@njpms.in	Bhatu	Done	Aug
Server	Configuration/Updation	Configuration parameters changed on NJAPPS Tomcat1, NJAPPS Tomcat2 and NJIMAGE Tomcat2.(Changed in PermSize Space) RAM Utilization improved after change.	Bhatu	Done	Aug
Server	Configuration/Updation	JDK 6.13 on NJAPPS	Bhatu	Done	Jul
RND	server	Tomcat 7 Problem Resolves – SingleThread Model	Bhatu	Done	Jul
Server	Configuration/Updation	Itext updated on Production	Bhatu	Done	Jul
RND	server	Jconsole – study and implementation on dev, test and prod servers	Bhatu	Done	Aug
Server	Monitoring	Monitoring tomcat servers	Bhatu	Done	Aug
Server	Monitoring	Solving tomcat 100% used problem – faz ledger Report	Bhatu	Done	Aug	identify, study & solve
Server	Monitoring	Solving tomcat 100% used problem – njdf report	Bhatu	Done	Aug	identify, study & solve
Application Architecture	Integration	Study and Implement WS from Java to Java	Nirali	Done	Jul
Application Architecture	Integration	Study and Implement WS from Oracle to Java	Nirali	Done	Jul
Application Architecture	Integration	Study and Implement WS from PHP to Java	Nirali	Done	Jul
Application Architecture	Integration	Study and Implement WS from PHP to PHP	Nirali	Done	Jul
Application Architecture	Integration	Itext Changes in ALL project for new Version	Nirali	Done	Jul
Server	Configuration/Updation	Study and Implement Jasper Reports	Nirali	Done	Jul
Application Architecture	Support	Change in on KYD Status from CAMS	Nirali	Done	Jul
Application Architecture	Support	Change in PDF Split Utility of Customer Care	Nirali	Done	Aug
Application Architecture	Audit	Regular Audit	Nirali	Done	Aug
RND	Initiative of New Technology	Studying Jconsole for per request memory	Nirali	Done	Aug